## Year Plan
Quarter | Goals | Start | End | Status
Quarter 1 | Archive IELTS from bank 6.5 to 7.0 | 2023-01-01 | 2023-03-31 | Done
Quarter 2 | Archive Developing Solutions for Microsoft Azure Certificate - AZ 204 | 2023-04-01 | 2023-06-30 | Done
Quarter 3 | Enhance knowledge about Microsoft Azure devops | 2023-07-01 | 2023-09-30 | In-Progress
Quarter 4 | Practice with real project for applying Microsoft Azure | 2023-10-01 | 2023-12-31 | To Do
| Goals | Goals
Quarter 1: Archive IELTS from bank 6.5 to 7.0
Practice Listening skill from 7.0 to 7.5
Practice Reading skill from 7.0 to 7.5
Practice Writing skill from 6.5 to 7.0
Practice Speaking skill from 6.5 to 7.0
Quarter 2: Archive Developing Solutions for Microsoft Azure Certificate - AZ 204
Complete Developing Solutions for Microsoft Azure on Udacity
Practice exam with question bank on udemy course
Quarter 3: Enhance knowledge about Microsoft Azure devops
Complete Cloud Devops using Microsoft Azure on Udacity
Quarter 4: Practice with real project for applying Microsoft Azure
Apply to job that using azure devops skill
Working in aglie software development

## Quater Plan
Quarter 3 | Enhance knowledge about Microsoft Azure devops
Week | <component> | Start | End | Status
2023-07-01 | Documentation about project | 2023-07-01 | 2023-07-06 | Done
2023-07-07 | Setup GitHub repository and azure devops repository | 2023-07-07 | 2023-07-13 | Done
2023-07-14 | Setup CI on GitHub Action | 2023-07-14 | 2023-07-20 | Done
2023-07-21 | Setup CD on Azure Pipeline | 2023-07-21 | 2023-07-27 | Done
2023-07-28 | Setup locust testing in local environment | 2023-07-28 | 2023-08-03 | Done
2023-08-04 | Demo project | 2023-08-04 | 2023-08-10 | Done
2023-08-11 | Waiting feedbaack from reviewer and apply change request from him | 2023-08-11 | 2023-08-17 | Done
2023-08-18 | Prepare new study phase 3 of azure devops course | 2023-08-18 | 2023-08-24 | In-Progress
| Goals | Goals
Documentation about project
Document in Read.me on Github
Create Architechture Diagram for full flow CI/CD
Create Project Plan - excel file
Create Trelo board
Instruction step to run project on azure app service, clone code from GitHub run testing
Note some enhancements can apply in future
Setup GitHub repository and azure devops repository
Clone and push code to Github
Generate ssh-key for connect from azure to GitHub
Study Azure Cloud Shell
Setup connection between GitHub and Azure Pipeline
Setup CI on GitHub Action
Setup Azure Cloud Shell
Setup environment for running cloud shell - resource group, blob storage,...
Add source code to cloud shell storage
Enable GitHub Action
Add yaml file to configure build step
Change configuration - init, lint, test
Add yaml file to configure build step
Verify result in log build
Setup CD on Azure Pipeline
CD with Azure Pipeline
Create connetion from azure devops to app service
Connect to github for clone source code
Enable CD on Azure Pipeline
Validate yaml file from github
Run pipeline
Testing after run pipeline successfull
Setup locust testing in local environment
Setup locust testing
Install locust on local environment
Run Testing for source code
Demo project
Instruction about setup enviroment and run project
Document to step setup environment
Document to step run project
Screenshot in each step
Waiting feedbaack from reviewer and apply change request from him
Apply change reviewer's request
Update document architecture with more details about CI/CD step
Add more logs for running deploy step
Prepare new study phase 3 of azure devops course
Review knowlegde about azure devops
Study more architecture's design pipeline
Research for enhancement point in this project